## Sheet1
TechConnect Project - Risk Register
|  | No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Response | Risk Owner | Probability | Impact | Status | Risk Response Strategy
| Initiating | Int1.1 | 1 | E prjt team | Early formation of project team | FF4 | A team needed to be created for this project and we generally know all of the members but we do not know their availiability | Uncertainty about team availability | Start creating the project contract. | PM Unit | high | low | Open | Acceptance
|  | Int1.2 | 2 | D prjt team | Delayed formation of project team | FF4 | A team needed to be created for this project and we generally know all of the members but we do not know their availiability | Team members' unconfirmed participation | Give the team members a deadline to respond if they will or will not participate with a mid-term reminder if needed. | PM Unit | low | medium | Open | Mitigation
|  | Int1.3 | 3 | F prjt team | Failure to form project team | FF4 | A team needed to be created for this project and we generally know all of the members but we do not know their availiability | Inability to form a complete team | Search for additional team members or consider outsourcing. | PM Unit | low | high | Open | Mitigation
| Planning | Plan1.1 | 4 | E prjt plan | Inaccurate estimation of project scope | FF4 | A project plan is to be submitted to the committee and its parts are being constructed by different team members. We are uncertain of each member's time management skills. | Lack of detailed planning or understanding of project requirements | Conduct thorough requirements analysis and engage stakeholders for input. | PM Unit | Medium | high | Open | Mitigation
|  | Plan1.2 | 3 | D prjt plan | Resource constraints | FF4 | A project plan is to be submitted to the committee and its parts are being constructed by different team members. We are uncertain of each member's time management skills. | Limited availability of resources (e.g., personnel, budget. | Prioritize tasks, allocate resources efficiently, and consider alternative resource options. | PM Unit | High | high | Open | Contingency Planning
|  | Plan1.3 | 1 | F prjt plan | Unrealistic project timelines | FF4 | A project plan is to be submitted to the committee and its parts are being constructed by different team members. We are uncertain of each member's time management skills. | Overly optimistic scheduling or underestimation of task durations | If the deadline for submission to the committee is missed, reassess the team member's position and potentially replace. Resubmit to the committee next year. | PM Unit | low | high | Open | Mitigation
|  | Plan2.1 | 2 | D committee | Scope creep during the planning phase | T | Evolving stakeholder expectations | Continuous changes in requirements. | Establish change control procedures, seek approval for scope changes | PM Unit | low | medium | N/A | Mitigation
|  | Plan2.2 | 1 | P Commite | Lack of stakeholder alignment | Planning | The plan for the online courses needs to be approved by the committee before the project can proceed. | Miscommunication or differing expectations among stakeholders | Regularly communicate project progress, gather feedback, and address concerns promptly. | PM Unit | Medium | high | N/A | Acceptance
Course Production - Phases 1 & 2 | Analysis, Pre-production & Planning | Ana1.1 | 3 | D course des packet | Inaccurate assessment of user needs | FF4 | Lack of complete team availability for user research | Insufficient data or understanding of user requirements | Conduct thorough user research, gather feedback, and iterate on prototypes. | PM Unit | low | medium | N/A | Mitigation
|  | Ana1.2 | 2 | T course des packet | Technology compatibility issues | FF4 | Unclear team availability for technology assessment | Compatibility issues between different technology components | Perform compatibility testing, engage with tech experts, and plan for contingencies. | Tech lead | high | high | N/A | Transference
|  | Ana2.1 | 5 | E course map | Early completion of course map | FF4 | The course map is incomplete until our meeting with the SME. We are unaware of the SME's schedules or when the course materials from course directors will be delivered. | Meeting with the SME and delivery of the course materials is early. | Adjust time, and add it to design and development of courses. | PM Unit | high | low | N/A | Acceptance
|  | Ana2.2 | 3 | D course map | Delay in completed of course map | FF4 | The course map is incomplete until our meeting with the SME. We are unaware of the SME's schedules or when the course materials from course directors will be delivered. | Meeting with the SME and delivery of the course materials misses deadline. | Set the second deadline for in 3 days and ask for daily progress reports from team members. Adjust time but taking it away from design and development. | PM Unit | low | medium | N/A | Mitigation
|  | Des1.1 | 6 | E SME | Design inconsistencies | FF4 | Lack of clear design guidelines or standards | Incomplete design specifications or changing requirements | Establish clear design guidelines and standards, conduct regular design reviews. | D Unit | medium | low | N/A | Acceptance
| Design | Des1.2 | 3 | D SME | User interface complexity | FF4 | Overly complex or confusing user interface design | User feedback indicating difficulties in navigation or usability | Simplify interface elements, conduct user testing for feedback and improvements. | D Unit | low | medium | N/A | Mitigation
|  | Des1.3 | 2 | F SME | Compatibility with multiple devices | FF4 | Failure to ensure compatibility across various devices and screen sizes | Testing on limited devices or overlooking responsive design principles | Conduct extensive device testing, prioritize responsive design implementation. | D Unit | low | high | N/A | Transference
| Development | Dvp1.1 | 3 | Technical skill gaps | Insufficient expertise | Tech | Insufficient technical expertise or skills within the development team | Encountering complex development tasks or new technologies | Provide training and skill development opportunities, consider hiring additional expertise. | D Unit | low | medium | N/A | Acceptance
|  | Dvp1.2 | 1 | F Software | Integration challenges | Tech | Difficulty integrating different system components or third-party services | Changes in integration requirements or unexpected dependencies | Conduct thorough integration testing, use standardized integration protocols. | D Unit | low | medium | N/A | Acceptance
|  | Dvp2.1 | 3 | F Software | Code quality issues | Dev | Lack of code review processes or coding standards | Poorly structured code, frequent bugs or errors | Implement code review practices, adhere to coding standards and best practices. | D Unit | low | medium | N/A | Acceptance
|  | Dvp2.2 | 1 | F course shell | Development Delays | Xmen | Unexpected setbacks in development tasks or resource constraints | Technical challenges, scope changes, or delays in deliverables from other teams | Monitor progress regularly, identify bottlenecks early, adjust resources or timelines as needed. | PM Unit | low | high | N/A | Acceptance
| Implementation/Production Close Out | Imp1.1 | 6 | E upload | Insufficient user training | Tech | Lack of comprehensive training programs for end users | Users facing difficulties in using the system effectively | Develop and deliver user training sessions, provide user guides and support materials. | TL Unit | medium | low | N/A | Acceptance
|  | Imp1.2 | 3 | D upload | Resistance to change | Tech | User reluctance or resistance to adopting new technology | Negative feedback or low user engagement during implementation | Communicate benefits of the new system, address concerns and provide support. | CML Unit | low | medium | N/A | Mitigation
|  | Imp1.3 | 1 | F upload | System downtime during deployment | Tech | Unforeseen technical issues causing system downtime | Disruption of operations or user experience during deployment1 | Perform thorough system testing, have rollback plans in place, and schedule deployments during low-traffic periods. | DL Unit | low | high | N/A | Escalation
|  | Imp2.1 | 5 | E train | Poor system performance post-implementation | FF4 | Inadequate system testing or optimization before going live | User complaints about slow performance or system errors | Monitor system performance, conduct performance testing, and optimize system resources as needed. | PM Unit | medium | low | N/A | Acceptance
| Evaluation | Eval1.1 | 5 | E eval | Inadequate performance metrics | FF4 | Lack of defined and measurable performance metrics | Difficulty in assessing project success or impact | Define clear performance metrics and KPIs, establish tracking mechanisms. | Eval Unit | high | low | N/A | Acceptance
|  | Eval1.2 | 3 | D eval | Delay in completion of evaluation and survey performance and format | FF4 | This is contingent on course creation which is determined by several schedulels between the ID and multi-media teammates who have different working schedules. | ID unit and MM unit turn in unti projects after first deadline. | Second deadline is set for 1 day and progress reports are requested. | Eval Unit | low | medium | N/A | Mitigation
|  | Eval1.3 | 2 | E eval | Failure of completion of evaluation and survey performance and format | FF4 | This is contingent on course creation which is determined by several schedulels between the ID and multi-media teammates who have different working schedules. | ID unit and MM unit turn in unti projects after second deadline. | Eval Unit creates a generic survey format to be submitted. | Eval Unit | low | medium | N/A | Acceptance
| PR & Marketing | PR1.1 | 3 | I PR | Increase in cost of PR materials | Xmen | Costs estimated in the project charter for PR materials may change after the project charter has been approved. | Cost of PR materials increased. | The program manager needs to find funds or decrease their order size from the PR unit. | PR Unit | low | medium | N/A | Acceptance
|  | PR1.2 | 5 | De PR | Decrease in the cost of PR materials | Xmen | Costs estimated in the project charter for PR materials may change after the project charter has been approved. | Cost of PR materials decreased. | The program manager can increase their order to cover the surplus in funds. | PR Unit | low | low | N/A | Acceptance
|  | PR2.1 | 5 | E PR delivery | Early delivery of PR materials | Xmen | Project content graphic package needs to be complete before PR materials can be created and delivered. | PR unit receives material on-time or early and is able to produce materials before the deadline. | PR has additional time to formulate further distribution possibilities. | PR Unit | medium | low | N/A | Acceptance
|  | PR2.2 | 3 | D PR delivery | Delay in delivery of PR Materials | Xmen | Project content graphic package needs to be complete before PR materials can be created and delivered. | PR unit receives the materials past the deadline by 24-hrs. Materials are created late. | PR has less time to formulate distribution possibilities. | PR Unit | low | medium | N/A | Acceptance
| Close-out of Project | Clo1.1 | 3 | D final | Delay in final project report creation | FF4 | Evaluation material needs to be completed before the project report can be created. All is contingent on if there no delays in the evaluation data being delivered to the project manager. | There is a 24-hr. delay in distribution evaluation material and delay in sending it to the project managere. | Project manager asks for an update from the Eval unit of when the end-semeter evaluations were distributed and when the data would be ready. | PM Unit | low | low | N/A | Acceptance
|  | Clo1.2 | 2 | F final | Failure in final project report creation | FF4 | Evaluation material needs to be completed before the project report can be created. All is contingent on if there no failures in the evaluation data being compiled and delivered to the project manager. | There is a 48-hr. delay in distribution evaluation material and delay in sending it to the project managere. | Data will be collected and sent to the project manager to compile the final project report. | PM Unit | low | medium | N/A | Acceptance
|  | Clo2.1 | 3 | D lessons | Delay in creating lessons-learned report | FF4 | Lessons-learned is dependant on the project report creation. If there are any delays in its creation it could delay the lessons-learned report creation. | There is a 24-hr. delay in creating the project report. | The project manager is given 48 hours to complete the report. | PM Unit | low | low | N/A | Acceptance
|  | Clo2.2 | 2 | F lessons | Failure to create lessons-learned report | FF4 | Lessons-learned is dependant on the project report creation. If there are any failures in its creation it could stop the lessons-learned report creation. | There is a 48-hr. delay in creating the project report. | The project manager submits the final project report to the committee and asks for a 24-hr. extension on the compiling of the lessons-learned report. | PM Unit | low | medium | N/A | Mitigation
|  |  | Risk Rank |  |  | Risk Abbreviations Key
|  |  | 1 | Disaster |  | D | Delay
|  |  | 2 | Dibacle |  | De | Decrease
|  |  | 3 | Issue |  | E | Early
|  |  | 4 | To be observed |  | F | Failure
|  |  | 5 | Minor success |  | I | Increase
|  |  | 6 | Success
|  |  | 7 | Excelsior! |  | Categories Key
[6 empty] | FF4 | Human Resources Internal
[6 empty] | Xmen | Human Resources External
[6 empty] | Tech | Technology
[6 empty] | T | Time